

**CoC Local Application Timeline – Revised**

**Federal Fiscal Year 2018**

**Updated: 8/2/18**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Due Date** | Task | **Responsible Party** |
|  | 7/27/18 | Local Project Applications released | CoC Staff |
|  | 8/10/18 | Local and E-Snaps Applications Due | Applicants |
|  | 8/14/18 – 8/16/18 | Funding Review Committee Meetings – Scoring/Ranking | Funding Review Committee, CoC Staff |
|  | 8/17/18 | Funding Review Committee Recommendations Shared With Applicants | CoC Staff |
|  | 8/20/18 | CoC Application Draft Posted Publicly | CoC Staff, CoC Members |
|  | 8/24/18 | Appeals Due, Changes Due in E-Snaps Applications | Applicants |
|  | 8/29/18 | Appeals Panel Meets (if required) | Appeals Panel |
|  | 8/30/18 | Funding and Ranking Recommendations Shared with Steering Council, Posted Publicly | CoC Staff |
|  | 9/6/18 | Public Feedback on Ranking and CoC Application Due to CoC Staff | CoC Staff |
|  | 9/7/18 | Steering Council Vote on Priority Listing Recommendations | Steering Council |
|  | 8/20/18 – 9/13/18 | Improvement to CoC Application | CoC Staff, CoC Members |
|  | 9/14/18 | CoC Application and Priority Listing Submitted to HUD | CoC Staff |